## Sheet1
Levels of Inspection
| Description | Inspection
1 | General Inspector Duties
| Receive Submittals | Expected
| Inspection of Materials to be Installed | Expected
| Material Testing | Expected
| Check Drainage Problems | Expected
| Traffic Control & Temporary Pavement Markings | Expected
| Check for any utility and structure conflicts | Expected
| Load Tickets: Check each load, information, temperature | Expected
| Collect tickets at end of day, total, compare to plan | Expected
| Check completed work after placement | Expected
| Measure Payment Quantities | Expected
| Prepare As-Builts | Expected
2 | Preconstruction Duties
| Receive, Review, Make Comments on Plans, Specifications | Expected
| Visit site and review project, document existing conditions | Expected
| Attend Preconstruction Meeting | Expected
3 | HMA Paving
| Base Course | Primary
| Intermediate Course | Primary
| Surface Course | Primary
| Verify widths, lengths, joint locations and yield | Secondary
| Paving area cleanliness | Secondary
| Tack: Coverage, temperature, material during Intermediate & Surface courses | Secondary
| Thickness, segregation | Secondary
| Verify castings to be adjusted and contractor has contacted utilities | Secondary
| Inspect lay out of widening area, mark base repair | Secondary
| check equipment on hand | Secondary
| Monitor core out | Secondary
| Check depth and slopes | Secondary
| Inspect sub-base compaction | Secondary
| Monitor Placement: Correct # of lifts, compaction, etc. | Secondary
| Material yield and thickness | Secondary
4 | Striping Layout
| Final layout and placement of pavement markings | Secondary
5 | Concrete Paving
| Check load batch time, material, segregation, slump, air | Primary
| Perform air tests | Primary
| Check Finishing: contraction and expansion joints, vibration, curing compound at time of placement | Primary
| Check ADA ramps for spec compliance | Primary
| Check for incorrect concrete placements to be replaced at no cost to Owner | Primary
| Check removal and layout: Before concret pour, check forms for depths, widths, reinforcing steel, etc. | Primary
| Verify Clean Up: form removal, backfilling, seeding, etc. | Secondary
| Check work the following day for any damage (vandalism) | Secondary
| Check equipment on hand | Primary
| Monitor Placement | Primary
| Material yield and thickness | Primary
6 | Milling
| Paint limits | Primary
| Verify removal of castings in milling areas | Secondary
| Monitor milling operation (check depth) | Secondary
7 | Structures (Pipe, Manhole/Inlet Reconstruction, New Structures)
| Check Plan with field condition | Primary
| Verify pipe sizes, structe types, etc. | Primary
| Alignment, slope, joints, connection to existing, etc. | Primary
| Backfilling and restoration | Primary
| Positive drainage | Primary
| Verify flow, drainage, and elevations | Primary
8 | Adjust/Remove & Reset Castings, Furnish Casting
| Verify Locations | Primary
| Verify removal is plated to prevent any accident | Primary
| Inspect condition of existing casting | Primary
| Check casting exposure to allow for surface placement or possible traffic hazard | Secondary
9 | Project Documentation, Close-out and Final Construction Record
| Inspector Daily Reports | Expected
| Weekly Reports ( to be submitted to the PM by noon the first day of the work week_ | Expected
| Pay Estimates | Expected
| Project Photographs (Before/During/After) | Expected
| As-builts | Expected
| Reports, Verification of all Installed Quantities, and Ticket Summary | Expected
| Material Certifications | Expected
10 | Structural Concrete
| Layout | Primary
| Verify Reinforcing Steel Layout | Primary
| Setting of New Structure | Primary
| Monitor backfilling | Primary
| Monitor Structure Removal | Secondary
| Check forms before concrete pour | Secondary
| inspect Subgrade before setting new structure for compaction | Secondary
11 | Traffic Signals
Coordinate through Project Manager and Traffic Eningeering for:
| Delivery and testing of the controller | Secondary
| Final inspection and activation of signal | Secondary
| Verify conduit and wire installation | Secondary
| Verify loop and sawing locations | Secondary
| Detector house installation | Secondary
Expected tasks are required to be completed in full and are pertinent to project performance.
Primary tasks represent tasks that require inspection throughout the entire duration of the task.
Secondary tasks represent tasks that require inspection intermittently throughout the duration of the task.

## Sheet2
Punchlist Checklist
Project:
File Number:
Inspector of Record
Inspector for Final Inspection:
Other City Inspectors:
Date of Final Inspection:
Contractors
Utilities Contractor:
Paving Contractor:
Other Contractors:
Sanitary Sewer Checklist
Castings set to proper grade
Chimney seals installed
Construction

## Sheet3
As-Built Checklist
Title Page (A Sheets)
Signature Block
Year Built
Contractor
Project Inspector
Correct Index Tabulation
Check to Include Revision Sheets
Typicals (B Sheets)
Correct Typicals
Add New Typicals Used
Quantity and Reference Information (C Sheets)
Correct Final Quantities
Add Contract Modifications
Correct Reference Information Notes
Add Contract Modification Reference Information
Line Out Quantities in Reference Information unless known to be correct
Plan and Profile Information (D through F Sheets)
Correct Right of Way Informaiton
Correct Alignment
Correct Ditch Grades
Correct Survey Information
Correct Utiltiy Information
Correct Access Information
Correct Drainage Details
Add Field Tile Information
Correct Removals and Work Done
Subgrade Treatment Areas
Utilties (M Sheets)
Correct Field Tile Crossings
Location, Size, and flow lines of storm and sanitary sewers and structures